## Sheet1
| 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06
Deadlines | 2019-05-28: Deadline interim report + initial presentation (Tue 4pm); skype at 1:15pm; 2019-06-06: deadline final report. presentation this day 9am LR6
Overall project tasks | 2019-05-18: set up git hub (needed for prototype design and experimental procedure version control) and everyone learn how to use; 2019-05-20: Stage 1: Testing of princples on standardized-geometry samples of metal blocks/ metal strips/ plastic strips. Test the principles of heat, UV, ethanol at different intensities, exposure time, etc; 2019-05-29: Stage 2: Test the prototypes: actually sterilize samples (cartridge and water sample container) Waterscope wants us to sterilize. Aim is to vary the parameters of the sterilization process given the prototype equipment (intensity/ exposure time etc) to obtain the best result.
|  |  |  | Design prototype (mechanical and electrical design) on CAD that would sterilize the actural cartirdge and container. Manufacture the prototype that can be used to steilise the actural cartidge and water sample container and ready to be tested by lab (may need several iterations) by 27th May | [12 empty] | report writing
|  |  |  | agree on this schedule |  |  | https://www.zotero.org integrate into report |  |  |  | finish the report | separate team into different part of the
[7 empty] | decide who will write what part of the report |  |  |  | book lab
Heat team | 2019-05-18: come up with list of equipment that needs purchasing to make the prototype and for stage 1 principle testing. maybe wise to buy several of the same for ease of prototyping e.g. several heater in case one breaks/ need redesign and old one is already welded; 2019-05-20: Design prototype (mechanical and electrical design) on CAD that would sterilize the actural cartirdge and container. Manufacture the prototype that can be used to steilise the actural cartidge and water sample container and ready to be tested by lab (may need several iterations) by 27th May; 2019-05-29: Redesign prototype if needed in light of result of the first set of test, manufacture another version of prototype to sterilize cartidge and water sample collector ready for 2nd set of test on 3rd June
|  | come up with experimental procedure (see template on drive, need creativity) for stage 1 of testing principle of dry heat: what parameters to change when sterilizing those standardised sample in dry oven (temperature and duration, anything else?) |  |  |  | characterise electroncal characteristics (reisstance, voltage nand current rating) of the heater | review lab results on feasibility test to inform design of prototype |  |  |  | order heating element, temperature censor
[6 empty] | place order for heating elements and thermometer needed for prototyping | find and order sutiabale thermometer |  |  |  | 3D resin to oder
UV team | 2019-05-18: come up with list of equipment that needs purchasing to make the prototype and for stage 1 principle testing. Source spectrometer; 2019-05-20: Design prototype (mechanical and electrical design) on CAD that would sterilize the actural cartirdge and container. Manufacture the prototype that can be used to steilise the actural cartidge and water sample container and ready to be tested by lab (may need several iterations) by 27th May; 2019-05-29: Redesign prototype if needed in light of result of the first set of test, manufacture another version of prototype to sterilize cartidge and water sample collector ready for 2nd set of test on 3rd June
|  | come up with experimental procedure (see template on drive, need creativity) for stage 1 of testing principle of UV: what parameters to change when sterilizing those standardised sample under UV light, (wavelength, intensity and duration, anything else?), how to position UV light |  |  |  | finish UV rig by 10am | review lab results on feasibility test to inform design of prototype
[5 empty] | cut out more plastic and metal blocks (currently looking at 8 more metal and 16 plastic, but will need to decide based on experimental procedures to be determined) | spectrum testing 3pm: characterise the UV bulbs as well as effectiveness of enclosure
[5 empty] | (This section has been updated as of 2230 21/05/19) | place order for UV bulbs of most effective wavelength and suitable geometry to be sued on prototyping), we need it ideally by Wed 22/5 but otherwise need another lab session on Mon to test it out
|  |  |  | manufacture UV enclosure for testing this for afternoon and wed |  | create 8 metal and acrylic sheet
|  |  |  | soldered wires to led bulbs |  | place order for polypropelene, make the blocks by Mon
[7 empty] | Decide whether to purchase further LEDs. Connect donated LEDs to PCB. |  |  |  | Lab testing of new bulbs
Lab team/ silver np/ ozone research | 2019-05-18: come up with experimental procedure template; 2019-05-20: Lab work 2-5pm: establish expreimental procedures (aka methodologies, protocol) to test the principle of different sterilization tehcniques (heat/ UV/ ethanol at different intensities/ exposure time etc) on standardized geometries samples; 2019-05-21: Lab work 4-5pm: collect result, then result analysis; 2019-05-22: lab work: first set of tests on the principle of heat and UV sterilization, following experimental procedures agreed with the heat and UV team; 2019-05-23: lab work: collect results; do UV test; 2019-05-27: overflow lab work and analysis of results; 2019-05-28: lab work: collect results; 2019-05-29: lab work: first set of parameter testing on the prototypes produced that use heat and UV (and ethanol) to steilize the actual cartridge and water collection container, following experimental procedures agreed with the heat and UV team; 2019-05-30: lab work: collect results; 2019-06-03: lab work: if permitted to use lab, do a second set of parameter testing on the prototypes produced that use heat and UV (and ethanol) to steilize the actual cartridge and water collection container, following experimental procedures agreed with the heat and UV team; 2019-06-04: lab work: collect results
|  | share research on ozone, continue research on ozone and silver np |  | write up protocol (swap and rinse technique); write up the tests done in the lab, procedures and result table | help draft UV and heat lab protocol | result analysis of results collected on 21/5 | result analysis: check with alex image processing |  |  |  |  | result analysis | lab: retest LED2; test under fume hood UV lamp; test for sensitiveity of swab and rinse with LB (transfer 10^5, 4, 3,2) bacteria onto the steel block and see how well it picks them up)
|  |  |  | test for spectrum of UV bulds given and effectiveness of enclosure |  |  | https://www.zotero.org integreate ito report
talked to heat team about design of prototype, agree lab protocol
ask EIEtl to lend us power source, find the missing UV led
What we need from each other and by when (constantly updated, delete things already obtained)
team requesting \ equipment or infomrtion from | 2019-05-18: Heat; 2019-05-20: UV; 2019-05-22: Lab; 2019-05-24: Waterscope
Heat | bar: 2019-05-18
UV | bar: 2019-05-20
Lab | 2019-05-20: metal blocks/ sheet by lunch 22/5; plastic blocks by next Mon; UV bulbs and rig by 10am 22/5; 2019-05-22: na; 2019-05-24: whether we can use lab 30-3rd
|  | - experimental procedure for testing feasibility of heat on standardised sample (including what parameters you would like us to change) [by Tue 21/5 evening] |  | - experimental procedure for testing feasibility of UV on standardised sample (including what parameters you would like us to change)[by Tue 21/5 evening] |  |  |  | O ring
|  |  |  | UV bulbs of desired wavelength that will be used on prototyping [Sunday evening 26/5] |  |  |  | data sheet for the 2 types of UV leds
how many are thye going to manufacture to work out cost benefit for making it disposable